## Thrive Ambitions - Action Plan
Thrive Delivery Plan 2019/20
1. Improved awareness and understanding amongst the public and professionals about children and young people’s emotional and mental health
Future in Mind: Workforce development
What will this look like in Salford? |  |  | Actions | Leads | Timescales
1.1 | Deliver on Green Paper expectations for improved mental health offer in schools, linked to Salford EHWB in schools programme (see 2.4 below) | 1.1.1 | Delivery of GM Healthy Schools Phase 2 in Salford Schools | Debbie Blackburn
|  | 1.1.2 | Support GM Mental Health in Education work programme | Debbie Blackburn
1.2 | Implementation of an ACEs pilot and training programme for Salford to support professionals in identifying trauma in childhood and building resilience | 1.2.1 | link into the wider Trauma and Adversity work | Jane Case | 31.03.20
|  | 1.2.2 | Deliver a conference on Adversity Trauma , risk and resilience | Jane Case | 31.03.20
|  | 1.2.3 | develop a training offer | Jane Case | 31.03.20
|  | 1.2.4 | engage wider partners and service areas including Adults provision | Jane case | 31.03.20
Priorities continued from last year:
1.3 | City-wide communications & engagement plan for children and young people’s emotional health | 1.3.1 | Annual refresh and implementation of joint communications and engagement plan (across SCC / CCG) and ongoing support | Vicky Pemberton | 31.03.20
|  | 1.3.2 | Mental health / CAMHS FAQs reviewed and published on the EHWB web pages | Shelley Bunting / Vicky Gillibrand | 31.08.19
1.4 | City-wide Workforce Development plan for frontline workers and professionals | 1.4.1 | Continue to roll-out the Salford Training offer | Jane Roberts | 31.03.20
|  | 1.4.2 | Evaluation of impact of training and identify gaps | Jane Roberts | 31.03.20
|  | 1.4.3 | Review and promote MindEd training modules; evaluate impact | Jane Roberts | 31.03.20
|  | 1.4.4 | Implement GM workforce strategy and continue to deliver CYP IAPT programme | Paul Wallis | 31.03.20
1.5 | Ensure access to quality on line self help info | 1.5.1 | Online information & resources including pathways developed for: Professionals webpage maintained (located on Salford City Partnership Website), Local Offer | Jane Roberts | 31.03.20
|  | 1.5.2 | Online information & resources including pathways developed for Children & Young people (located on WUU2 website), including use of videos | Suzanne Quigley / Jane Roberts | 31.03.20
|  | 1.5.3 | EHWB online directory updated and promoted across all providers / services | Jane Roberts | 31.03.20
|  | 1.5.4 | Parents / carers web pages to be developed with details of Parent Peer Support Group Project and further related info | Lucy Sutcliffe | 31.03.20
|  | 1.5.5 | Review and evaluate impact of online information and resources | Jane Roberts | 31.03.20
2. Children and young people in Salford have timely access to effective child-centred emotional and mental health support when they need it
Future in Mind: Resilience, prevention and early intervention; Improving access to effective support
What will this look like in Salford? |  |  | Actions | Leads | Timescales
2.1 | Early Help implementation plan and rollout city wide | 2.1.1 | Create action plan with the Early Help Working Group | Lucy Sutcliffe | 31.03.20
|  | 2.1.2 | Support 42nd St with recruitment for Development Days | Lucy Sutcliffe | 31.03.20
|  | 2.1.3 | 42nd Street to deliver Development Days to support early help development city wide and workforce development in this context (all partners included). | Simone Spray
2.2 | Develop strategies to better support young people not in education, employment or training (NEET) with improved emotional wellbeing | 2.2.1 | Actively promote 42nd St online counselling offer to YP who NEET | Sarah Scanlan
|  | 2.2.2 | Monitor of proportion of cohort with MH needs in Q1 and Q3 | Sarah Scanlan | 31.03.20
|  | 2.2.3 | Encourage more post 16 providers and services to engage with EFS | Helen Nicolle | 31.03.20
|  | 2.2.4 | Audit training needs of neet workforce | Sarah Scanlan | 31.12.19
Priorities continued from last year:
2.3 | To develop a whole school approach to EHWB | 2.3.1 | Continue engagement of schools in phase 3 of CAMHS / Schools link project, and the i-reach service, across Salford | Jane Davies | 31.03.20
|  | 2.3.2 | Continue to encourage schools to use the Approved Provider Register for counselling in schools | Emily Edwards | 31.03.20
|  | 2.3.3 | Deliver and evaluate school counselling small grants programme (Population Health fund) | Emily Edwards | 31.12.19
|  | 2.3.4 | Undertake review of CYP counselling provision in Salford to inform future commissioning plan | Emily Edwards | 31.03.20
|  | 2.3.5 | Continue development and delivery of the Little Pot of Health, Healthy Schools Fund | Stephen Woods | 31.03.20
|  | 2.3.6 | Continue to engage schools in the emotionally friendly schools accreditation | Helen Nicolle | 31.03.20
|  | 2.3.7 | Implement Early Years and post 16 versions of the emotionally friendly schools programme | Helen Nicolle | 31.03.20
|  | 2.3.8 | Review and monitor the use of primary to secondary school transition processes and good practice standards to ensure they meet the needs of all pupils, particularly vulnerable pupils, | Helen Nicolle | 31.03.20
|  | 2.3.9 | Develop a peer to peer leadership approach of support and training for school leaders | Zandra Wilkinson | 31.03.20
|  | 2.3.10 | Develop options to promote EHWB support for pupils not in mainstream schooling - i.e alternative provision and EHE | Helen Nicolle | 31.03.20
2.4 | Embed THRIVE approach in Salford | 2.4.1 | Co-ordinate Salford Thrive network (virtual) and hold 2-3 Thrive events each year (October/March/May) | Jane Roberts/Emily Edwards | 31.03.20
|  | 2.4.2 | Contribute to GM i-Thrive work, including Thrive Leads and i-thrive Academy | Emily Edwards | 31.03.20
2.5 | Improved access to effective support | 2.5.1 | Mainstream the Single Point of Contact Pilot in CAMHS through the CAMHS service review | Emily Edwards | 31.03.20
2.6 | Integrated approach between Children's and Adult commissioning and mental health services for young people aged 18-25 to ensure effective transition support | 2.6.1 | Continue to monitor transitions from CAMHS to AMHS & other adult services. Consider an enhanced transition period for vulnerable groups e.g. up to age 19 or 25. Potentially a focus on those people 16-25 accessing IAPT. | Emily Edwards / Clare Mayo | 31.03.20
|  | 2.6.2 | Further develop the 16-25 Multi Agency Hub pathway and policy for young people with disabilities and/or complex and mental health needs | Caitlin Chapman | 31.03.20
|  | 2.6.3 | Review specific needs and develop pathway for care leavers to build resilience and coping strategies in preparation for adulthood | Phil Varghese/Emily Edwards | 31.07.19
19
Future in Mind: Care for the most vulnerable
What will this look like in Salford? |  |  | Actions | Leads | Timescales
3.1 | Integrated Neuro-Development Pathway developed and implemented, aligning with GM ADHD standards | 3.1.1 | Recruit coordinator/s to run the pathway | Lucy Sutcliffe | 31.03.20
|  | 3.1.2 | Undertake mapping of Neurodev suitable courses and interventions and create user friendly database or webpage | Lucy Sutcliffe | 31.03.20
|  | 3.1.3 | Plan and set up Core Group Panel for the Pathway | Lucy Sutcliffe | 31.03.20
|  | 3.1.4 | Monitor and evaluate the delivery and outcomes | Lucy Sutcliffe | 31.03.20
3.2 | Implementation and review of GM Crisis Care pathway for children and young people | 3.2.1 | Monitor and evaluate All Age Liaison service | Emily Edwards/ Emma Hinchcliffe | 31.03.20
|  | 3.2.2 | Implementation and monitoring of Safezones | Emily Edwards / Simone Spray | 31.03.20
|  | 3.2.3 | Implementation of Rapid Response Teams | Emily Edwards | 31.03.20
|  | 3.2.4 | attendance and contribution to GM CCP Steering Group | Emily Edwards | 31.03.20
3.3 | Continue to deliver on the Suicide Prevention Strategy | 3.3.1 | Respond CDOP actions in line with Suicide Prevention Strategy / Support CYP and Exam Stress comms plan / align Papyrus training with wider suicide prevention training strategy | Clare Mayo/Jane Roberts | 31.03.20
|  | 3.3.2 | Undertake Salford thematic review for CYP suicide and identify areas for development under the Suicide Prevention Partnership | Jane Roberts/ Emily Edwards | 31.03.20
3.4 | Monitor and evaluate the Manchester and Salford Eating Disorder service, aligned to GM Peer Review | 3.4.1 | Monitor the service using KPIs directed by national requirements and evaluate in partnership by peer review | Lucy Sutcliffe | 31.03.20
|  | 3.4.2 | Implement recommendations from GM peer review | Lucy Sutcliffe | 31.03.20
Priorities continued from last year:
3.5 | Monitor and evaluate targeted pilots | 3.5.1 | Monitor and evaluate Online Therapeutic Support Innovation Pilot | Simone Spray / Emily Edwards | 31.07.19
|  | 3.5.2 | Monitor and evaluate Integrated Community Response Service pilot commissioned in Salford and Manchester to inform future commissioning Plans | Simone Spray / Emily Edwards | 31.03.20
|  | 3.5.3 | Deliver LGBTQIA action plan including: Charter marks - promote and engage services to implement Pride in Practice, Rainbow Flag award and You're Welcome LGBTQIA awareness training for professionals Roll out of schools training and LGBT+ resource pack Big Lottery funding application for LGBT+ youth project | Jane Roberts | 31.03.20
|  | 3.5.4 | Deliver VCSE MH funded OJC mental health project (year one of 3) | Simone Spray | 31.03.20
4. Parental support and programmes for those who need it
What will this look like in Salford? |  |  | Actions | Leads | Timescales
4.1 | Delivery of the Parent Peer Support Group Project | 4.1.1 | Set up steering group and agree terms of reference | Lucy Sutcliffe | 31.03.20
|  | 4.1.2 | Establish comms plan and agree wording with delivery partner | Lucy Sutcliffe | 31.03.20
|  | 4.1.3 | Monitor delivery | Lucy Sutcliffe | 31.03.20
|  | 4.1.4 | Support as nec through the year with training and development needs | Lucy Sutcliffe | 31.03.20
4.2 | Continued delivery and review of Homestart Salford and Trafford project | 4.2.1 | Evaluation and review sustainability aligned to PIMH programme (4.3 below) | Emily Edwards | 31.03.20
4.3 | Implement Perinatal Infant MH pathway, aligned to GM standards | 4.3.1 | Develop business case for Parent / infant attachment service | Clare Mayo/Michelle Whittaker | 31.03.20
|  | 4.3.2 | Monitor progress against the IAPT perinatal action plan | Clare Mayo/Michelle Whittaker | 31.03.20
5. Transparency and accountability across the whole system
Future in Mind: Accountability, transparency & governance
What will this look like in Salford? |  |  | Actions | Leads | Timescales
5.1 | Further alignment and Integration of CAMHS commissioning arrangements and contracts | 5.1.1 | Annual review of GM specification and variation into contract | Emily Edwards | 31.03.20
|  | 5.1.2 | Review of targeted services and GM specification addendums varied into contract | Emily Edwards | 31.03.20
|  | 5.1.3 | Pooled budget and integrated contract for CAMHS | Emily Edwards | 31.03.20
5.2 | Continue engagement and communications with GPs around CYP mental health and Thrive | 5.2.1 | Lucy / Jane to Liaise with Wan-ley re actions | Lucy / Jane / Wan-ley Yeung | 31.03.20
|  | 5.2.2 | Regular items in GP newsletter | Lucy / Jane / Wan-ley Yeung | 31.03.20
|  | 5.2.3 | Input to GP engagement events | Lucy / Jane / Wan-ley Yeung | 31.03.20
|  | 5.2.4 | GPs as part of Thrive Network | Lucy / Jane / Wan-ley Yeung | 31.03.20
5.3 | Continuation of the Thrive (EHWB) Partnership as the expert reference group to help shape and deliver the priorities | 5.3.1 | Bi-monthly meetings | Emily Edwards | 31.03.20
|  | 5.3.2 | Sub Groups and Task and Finish groups as required: LGBT, Comms and Engagement, Transitions, Parent Support, Education, CYP Engagement , Produce quarterly EHWB/CAMHS dashboard to monitor progress | Emily Edwards / Lucy / Jane | 31.03.20
6. Children and Young People have a voice
Future in mind: Involvement of children & young people
What will this look like in Salford? |  |  | Actions | Leads | Timescales
6.1 | Children and Young people are involved in the development, delivery and evaluation of services | 6.1.1 | Task and finish group to establish action plan and feed into 0-25 CYP engagement plan / Salford CYP Voice work | Lucy Sutcliffe | 31.03.20
|  | 6.1.2 | Establish links with GM CYP mental health forum and activity | Lucy Sutcliffe | 31.03.20
|  | 6.1.3 | Improved engagement with CYP across the system (Schools, colleges, IYSS, commissioned services). Consider annual comms - you said, we did… | Lucy Sutcliffe | 31.03.20
|  | 6.1.4 | Continued involvement of LGBTQ+ young people in the working group. | Jane Roberts | 31.03.20